## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-00 | As a team, we need to collaborate on a Shared Learning Repo to practice Python/Pandas. Propose business logic functions charts, graphs and plots. | Must Have | None | All Team | 3- Completed
Sprint 2 | Sprint 2 | US-01 | As a lead, I want to initialize the Main Project Repo with a VS Code Environment. | Must Have | None | Saidul | 3- Completed
Sprint 2 | Sprint 2 | US-02 | As a user, I want a Data Upload Page to load traffic CSVs. | Must Have | US-01 | Divija | 3- Completed
Sprint 2 | Sprint 2 | US-03 | As a system, I need Feature-Branch workflows to manage 15 devs. | Must Have | None | Anshu | 3- Completed
Sprint 3 | Sprint 3 | US-08 | As a user, I want Home & About Pages for project info. | Must Have | US-01 | Ishwari | 3- Completed
Sprint 3 | Sprint 3 | US-04 | As a user, I want distinct Visualization Pages for different insights. | Must Have | US-02 | Divija | 3- Completed
Sprint 3 | Sprint 3 | US-05 | As a user, I want Visual Plots (Bar/Pie) for traffic trends. | Must Have | US-04 | Harika | 3- Completed
Sprint 3 | Sprint 3 | US-06 | As a user, I want Scatter & Bar Plots for variable correlation. | Must Have | US-04 | Poojitha | 3- Completed
Sprint 3 | Sprint 3 | US-07 | As a user, I want Donut Charts for violation composition. | Should Have | US-04 | Anshu | 3- Completed
Sprint 3 | Sprint 3 | US-08 | As a user, I want Risk & Heatmap Plots for severity analysis. | Must Have | US-04 | Divija | 3- Completed
Sprint 4 | Sprint 4 | US-09 | As a brand, I want a custom Logo and Platform Identity (CollisionX India). | Should Have | None | Mrunalini | 3- Completed
Sprint 4 | Sprint 4 | US-10 | As a user, I want a Map Visualization using specific GeoJSONs for accurate regions. | Must Have | US-02 | Saidul | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 98 | 8 | 9 | 8 | 11 | 10 | 2 | 0 | 5 | 8 | 8 | 10 | 8 | 8 | 3
SPRINT 1 BACKLOG
US-00 | T-101 | Python/Pandas Learning | 2025-10-17 | 2025-10-23 | All | Learning | 3- Completed | 6 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-00 | T-102 | VS Code Env Deployment | 2025-10-17 | 2025-10-18 | Saidul | Setup | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-00 | T-103 | Git Basics Set Up | 2025-10-24 | 2025-10-26 | Anshu | Build | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0
US-00 | T-104 | Shared Repo Collab | 2025-10-27 | 2025-10-29 | All | Coding | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1
US-00 | T-105 | Project Ideation | 2025-10-30 | 2025-10-30 | All | Build | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
SPRINT 2 BACKLOG
US-01 | T-201 | Main Repo Initialization | 2025-10-31 | 2025-11-02 | Saidul | Dev/Ops | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-202 | Branch Protection Rules | 2025-11-01 | 2025-11-03 | Anshu | Config | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-203 | Data Upload Page | 2025-11-04 | 2025-11-07 | Divija | Dev | 3- Completed | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-204 | CSV Encoding Fixes | 2025-11-08 | 2025-11-10 | Divija | Bugfix | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-04 | T-205 | Data Utility Scripts | 2025-11-10 | 2025-11-13 | Vijay | Dev | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0
SPRINT 3 BACKLOG
US-04 | T-301 | Viz Page Architecture | 2025-11-14 | 2025-11-18 | Ishwari | Design | 3- Completed | 6 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-302 | Sidebar Navigation Fix | 2025-11-17 | 2025-11-18 | Poojitha | Refactor | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-303 | Basic Bar/Pie Charts | 2025-11-16 | 2025-11-19 | Sanjana | Dev | 3- Completed | 6 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-304 | Heatmap Implementation | 2025-11-22 | 2025-11-24 | Saniya | Dev | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0
US-08 | T-305 | Home & About Pages | 2025-11-23 | 2025-11-27 | Ishwari | Dev | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0
SPRINT 4 BACKLOG
US-09 | T-401 | Logo & Identity Design | 2025-11-28 | 2025-11-30 | Mrunalini | Design | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-402 | GeoJSON Map Implementation | 2025-12-01 | 2025-12-06 | Saidul | Dev | 3- Completed | 6 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-10 | T-403 | Map Validation & Fixes | 2025-12-06 | 2025-12-08 | Saidul | Unit Test | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0
US-11 | T-404 | Cross-Browser QA | 2025-12-07 | 2025-12-10 | Mounika | System Test | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0
US-12 | T-405 | Final Documentation | 2025-12-09 | 2025-12-11 | Saidul | Others | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sp 1 | Day 2 (Oct 18) | Planning: Initial project planning. | Decision: Concluded to build a Python-heavy project to maximize learning (avoiding simple no-code tools).
Sp 1 | Day 6 (Oct 22) | Info: Reviewing the overall Project Structure. | Action: Walkthrough of the folder structure (core/, pages/) so everyone understands the flow.
Sp 2 | Day 16 (Nov 01) | Planning: Graphic Plots strategy. | Decision: Decided which specific libraries (Matplotlib/Seaborn) to use for which insights.
Sp 2 | Day 23 (Nov 08) | Blocker: Team Confusion on Architecture. | Action: "Clean-the-air" meeting to resolve doubts about where to put logic vs UI code.
Sp 3 | Day 30 (Nov 15) | Issue: Frequent merge conflicts overriding code updates. | Action: Anshu enforced "Branch Protection Rules" requiring PR reviews before merge.
Sp 3 | Day 37 (Nov 22) | Demo: Teammates proposed new features (Home/About/KYD). | Action: Accepted proposals: Ishwari assigned Home/About, Mrunalini assigned 'Know Your Data' (Numerical Analysis).
Sp 4 | Day 44 (Nov 29) | Review: UI Consistency Check (HTML/CSS). | Action: Mrunalini & Ishwari established global CSS variables to fix table rendering issues.
Sp 4 | Day 51 (Dec 06) | Review: Final Draft Demonstration. | Action: Reviewed the nearly-finished product; requested minor preference-based UI tweaks before freezing code.
Sp 4 | Day 56 (Dec 11) | Prep: Presentation & Live Demo planning. | Action: Assigned roles for the final presentation: who speaks on Architecture, who does Live Demo, etc.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 2 | 2025-10-27 | 2025-11-09 | Anshu | Grouping PRs by Feature Branch (UI, Data, Core). | Allowing direct commits to Main. | Managing the shared repository protections. | Enforced Branch Protection Rules requiring reviews.
2 | Sprint 2 | 2025-10-27 | 2025-11-09 | Divija | checking file encoding (UTF-8 vs Latin-1). | Assuming all CSVs are clean. | Writing robust data loader tests. | Added try-except block for encoding errors in utils.py.
3 | Sprint 3 | 2025-11-10 | 2025-11-23 | Saidul | Leveraging Gemini/Claude for tricky Pandas debugging. | Writing custom CSS without checking Streamlit support. | guiding the 15-member team on architecture. | Scheduled AI-debugging sessions for complex errors.
4 | Sprint 3 | 2025-11-10 | 2025-11-23 | Mrunalini | Creating assets (Logo) earlier in the sprint. | Using hardcoded paths. | improving UI aesthetics. | Established assets/ folder standard for all images.
5 | Sprint 3 | 2025-11-10 | 2025-11-23 | Ishwari | Testing dashboard on Window resizing. | Designing only for maximized Desktop view. | Explicitly defining width parameter (fixing deprecation issue). | Resolved layout breaks by manually setting chart width.
6 | Sprint 3 | 2025-11-10 | 2025-11-23 | Poojitha | Using relative path keys for navigation. | Hardcoding page filenames in links. | Modularizing the Sidebar code. | Refactored sidebar.py to be robust against file renaming.
7 | Sprint 4 | 2025-11-24 | 2025-12-07 | Saidul | Validating GeoJSON files before implementation. | Ignoring projection errors. | searching for open-source resources. | Implemented specific GeoJSON validation step in map_plot.py.
8 | Sprint 4 | 2025-11-24 | 2025-12-07 | All | Using standard Variable names (Data Variables). | Hardcoding column names in pages. | collaborating on plotting logic. | Refactored all page hardcoding to usage of data_variables.py.
9 | Sprint 4 | 2025-11-24 | 2025-12-07 | Mounika P | Cross-browser testing (Chrome/Edge/Firefox). | Waiting for DEV completion to start QA. | Logging defects in the shared Tracker. | Identified 2 critical UI bugs (BUG-03, BUG-06) before final demo.