## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
BUG-01 | Anshu | 2025-11-02 | Merge Conflict: Logic overwrites in app.py. | Sprint 2 | Anshu | Maintainability | Restricted main branch; enforced 7-branch workflow. | 2025-11-03 | Closed | Process Updated
BUG-02 | Divija | 2025-11-05 | Encoding Error: CSVs with special chars failing. | Sprint 2 | Divija | Logical | Added latin-1 fallback in utils.py. | 2025-11-06 | Closed | Critical Fix
BUG-03 | Mounika P | 2025-11-18 | Visuals: Bar charts overlapping. | Sprint 3 | Sanjana | User Interface | Adjusted figure size and rotation using Matplotlib params. | 2025-11-19 | Closed | Verified
BUG-04 | Darsana | 2025-11-20 | Analysis: Complex filters causing slow load. | Sprint 3 | Darsana | Standards | Optimization assistance from AI tools (Claude). | 2025-11-21 | Closed | Optimized
BUG-05 | Mounika P | 2025-11-22 | UI Glitch: Sidebar overlapping text. | Sprint 3 | Ishwari | User Interface | Applied custom CSS media queries. | 2025-11-23 | Closed | Verified
BUG-06 | Saidul | 2025-12-01 | Map Visibility: Map not loading for certain States. | Sprint 4 | Saidul | Maintainability | Swapped broken GeoJSON with valid Open Source files. | 2025-12-02 | Closed | Fixed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others